## requirements
LISTED BLUE
website Backlog
our site includes: | must | later | no
registration |  |  | √
signin
search function
breadcrumb navigation
shopping cart
check out
accepts payment methods: cc, paypal, btc, ideal, direct bank transfer ... Make your payment directly into our bank account. Please use your Order ID as the payment reference. Your order won’t be shipped until the funds have cleared in our account. Holding of Items Pending Purchase Items purchased by “Direct to Bank” payment could possibly be sold to another while we are waiting for the payment to be received or cleared. This would be extremely rare but possible. We cannot hold items due to the problem of people placing orders for items and never completing the purchase. If you want to request an item to b
order tracking
currencies: USD, EUR, BTC, etc
shipping options: DHL, UPS, etc
procut order realitey / oplage teller
product categories
sections: home, products, about, contact
feedback form
incorporate social media: twitter, fb, pinterest, instagram
comments / rate prodcts
CMS to upload products
magnifying glass for product zoom in http://www.mind-projects.it/projects/jqzoom/demos.php
Visual:
single page scroll (http://www.thepetedesign.com/demos/onepage_scroll_demo.html#1)
responsive
100% images
http://www.addthis.com/for/wordpress
http://modernizr.com/
http://codecanyon.net/item/woocommerce-one-page-shopping/7158470
http://www.woothemes.com/woocommerce/
http://themeforest.unitedthemes.com/wpversions/brooklyn/elegant/
http://www.smashingmagazine.com/2014/02/13/create-client-side-shopping-cart/ | tutorial shopping cart
http://www.htmlgoodies.com/beyond/javascript/article.php/3471331 | tutorial shopping cart
a-frames
mertens amsterdam
webdesign examples
http://melanie-f.com/ | homepage movie
http://lsm.com/ | full image homepages; in comes the navigation
http://www.kirschnerbrasil.cc/
http://charactersf.com/
http://thecharlesnyc.com/
http://danielladraper.com/ | brits juwelery ... Could be something to look at
http://makedirectory.co/ | japanese style ...
http://www.iamnotchinese.co/ | one pager shop
http://phones.matiasgallipoli.com/ | one pager shop
http://www.madebysix.com/
how to present object & photoprint?
http://www.pictureframes.com/Ready-Made-Wood-Picture-Frames | online picture frame shop
http://framefinders.com/antique-frames/all/american-arts-and-crafts-antique-frame-4/ | legendary antique frame shop
http://www.a-frames.nl/en// | frame maker nl wormerveer
photograph photoprint in interior ... How to standardise?
http://www.pixpa.com/ | full screen carousel homepage

## people
job smeets
cok de rooij
hella jongerius
judith cahen
gijs stork
melvin moti | via lawrence

## packages
how can i help?
A | name on website
ambassador, speak on behalve of
be present at pr events
buy product
testimonials (for website)
support act
auction

## screen resolutions
| Resolution (portrait) |  | aspect ratio
Device | width | height
iPhone 5s | 640 | 1136 | 1: | 1.775
Samsung Galaxy S4 | 1080 | 1920 | 1: | 1.7778
Samsung Galaxy S3 | 720 | 1280 | 1: | 1.7778
iPhone 4 | 640 | 960 | 1: | 1.5
iPhone 6 * | 750 | 1334 | 1: | 1.7787
Samsung Galaxy S5 | 1080 | 1920 | 1: | 1.7778
iPad | 768 | 1024 | 1: | 1.3333
iPad Retina | 1536 | 2048 | 1: | 1.3333

## provenance
Title | Pet name | Description | Materials | Dimensions | Signed, Dated, Numbered | Provenance | Image shot (Conceived) | Purchase date | Price | Store
? ListedBlue No. 01 | Inktpotje |  |  |  |  | Thrift store Amsterdam | do 5 Jun. 2014 | 22 May. 2014 | 0.5 | Het Juttersdok, Zeeburgerpad 90-99, Amsterdam | Nanda
? ListedBlue No. 02 | Zen stone (ListedBlue.tiff) |  | Welke steensoort? |  |  | Thrift store Amsterdam | do 5 Jun. 2014 | 31 May. 2014 | 1.75 | Rataplan, Willem Roelofstraat 2, Amsterdam
| Japans | Rode geglazuurde bak (asbak?) met schoefafdrukken erin |  |  |  | Thrift store Amsterdam | do 12 Jun. 2014 | 02 Jun. 2014 | 1.5 | De Locatie, Distelweg 85, Amsterdam
| Pukkelman (Pikachu) |  |  |  |  | Thrift store Schiedam |  | 12 Jul. 2014 | 3 | Kringloop Gewoon Goed, Schiedam
| Lolliepot | Bakje van ijsstokjes | Welke houtsoort? |  |  |  | 26 Jun. 2014 …? |  |  | Martine ?
| Vaasmand Tiny '95 | Aardewerk bak met groene griezels bovenop |  |  | Tiny '95 on the verso |  | 26 Jun. 2014 …? |  |  | Martine ?
| Witte asbak | Wit marmeren/albast asbak? |  |  |  | Thrift store Nijverdal |  |  |  | Dorcas Nijverdal, met z'n 3-en geshopt
| Schetstafelkleed | Linnen tafelkleed, borduursel, onaf | [7 empty] | ??
Martine ?
| DSC_2691 | Houten bak bij Terre des Hommes, 's Hertogenbosch |  |  |  | Thrift store 's Hertogenbosch |  | 09 Aug. 2014 | 5 | Terre des Hommes, 's Hertogenbosch
| DSC_2610 | Bruine gekleide schaal met duimafdrukken erin |  |  |  | Thrift store Amsterdam |  | 27 Jun. 2014 | 13 | The Oddity Shop, Amsterdam
| DSC_2682 | Houten doosje, dicht | Welke houtsoort? |  |  | Thrift store Amsterdam |  | 13 Jun. 2014 | 1.5 | Juttersdok, Postjeskade 23-25, Amsterdam
| DSC_2639 | Varkensblaas | [7 empty] | Stef/Martine
| DSC_2612 | Scheef vaasje met horizontale streepjes groen en … |  |  |  | Thriftstore Arnhem |  | 03 Jul. 2014 | 0.5 | 2Switch, Westervoortsedijk 120, Arnhem
| DSC_2611 | Scheef kommetje, zwart | [5 empty] | 24 Jul. 2014 | 3 | Rataplan, Willem Roelofstraat 2, Amsterdam
|  | Groen glazen vaastje |  |  |  | Thrift store Amsterdam |  | 13 Sep. 2104 | 25 | May Antiek, Nieuwe Spiegelstraat 25, Amsterdam
|  | Schilderijtje met kerk en koeien |  |  |  | Thrift store Amsterdam |  | 13 Sep. 2104 | 7 | Brahim, Jan Hanzenstraat 58-60
? | DSC_2622 | Asbak rood/roze marmer |  |  |  | Thrift store Amsterdam |  | 23 Jun. 2014 | 5 | Juttersdok, Postjeskade 23-25, Amsterdam
? | DSC_2646 | Tinnen bordje |  |  |  | Thrift store Amsterdam |  | 19 Mrt. 2014 | 3 | Rataplan, Willem Roelofstraat 2, Amsterdam
|  | Houten lineaal |  |  |  | Thrift store Amsterdam |  | 10 Jun. 2014 | 0.5 | Juttersdok, Postjeskade 23-25, Amsterdam
| DSC_2645 | Mok met foto man met baby, bij kopieerwinkel gemaakt (Thailand?) |  |  |  | Thrift store Amsterdam |  | 27 Jun. 2014 | 0.5 | De Locatie, Camperstraat 42 Amsterdam
? | DSC_2693 | Vestje baby, SFG | [7 empty] | Frankrijk ?
? | DSC_2609 | Gekleid asbakje, zwart met wit geglazuurde binnenkant |  |  |  | Thrift store Amsterdam |  | 24 Jul. 2014 | 1.75 | Rataplan, Willem Roelofstraat 2, Amsterdam

## status
currently on offer ...
speaking with ...
email out to ...
location live ...
last social update (twitter, etc)
last source ...
latest adoptation ...

## backlog
[7 empty] | bug | urgent | open
[7 empty] | improvement | high | in progress
[7 empty] | feature | low | resolved
content
NR | DESCRIPTION | TYPE | PRIO | STATUS | ASSIGNED | REMARK
1 | replace logo header with image file | improvement | urgent | resolved | stef | found new font type "Lustria"
2 | find replacement icon font for 'x' close button close store | improvement | urgent | resolved | stef | found new icon font untitled but cant import in code
3 | finalise content copy | content | urgent | in progress | SFG
4 | all products | content | high | in progress | SFG / SJJ
5 | about | content | high | in progress | MS
6 | terms of service | content | high | in progress | SJJ
7 | QandA | content | high | in progress | SFG
8 | replace Propertius Duskywing image (1px white line) | content | urgent | resolved | SFG
9 | replace menu icon with close icon when shop open | improvement | high | resolved | RN
10 | styling css shop layout | improvement | urgent | in progress | SFG
11 | implement class for black image background (silver birch) | improvement | high | resolved | RN | json: textcolor … light / dark
12 | magnifier glass for even bigger picture | feature | low | open | RN
13 | email enquiry button per product/embodiment | feature | high | resolved | RN
14 | landing page template markup, css & content | content | urgent | in progress | SFG
15 | menu nav structure templates designs, markup, css | improvement | urgent | in progress | RN | what is mean here?
16 | solution swipe/click portrait mode | bug | urgent | resolved | RN | javascript onclick not ontouch
17 | z-index product navigation title | bug | urgent | resolved | RN
18 | scroll/swipe indicator | feature | low | open | RN
19 | clean up _landing.css, finish landing page (mobile first) | content | urgent | in progress | SFG
20 | add unique id's (upper roman) to all products, sort on id display | feature | high | open | SFG / RN
21 | add product ID / name to mailto Enquiry tag | improvement | high | in progress | RN
22 | items sold functionality & visual design | feature | low | open | SFG / RN
23 | loading product title on collection.html delayed? | improvement | low | open | RN
24 | firefox mobile (android) content twitch / white gap on top page | bug | low | open | RN | The browser as of July 2014 only has 0.69% of the mobile/tablet market share
25 | ios collection.html fix body floats in window | bug | high | open | RN
26 | portrait mode click to next product fix 1st center current product | bug | low | open | RN
27 | move object info in store page to center collumn? | improvement | high | resolved | SFG | discussed with girls, agreed, done
28 | implement method to link/share product specific page in collection | feature | high | open | SFG / RN
29 | resize landing page images (object,image,download) | improvement | high | open | SFG | way too big right now
30 | style css for IOS device | improvement | high | in progress | SFG
31

## models
|  | prints | 3d prints | object costs | object rev | print costs | print revenue | 3d pr costs | 3d pr revenue
products | objects | 10 | 0 | 100 | 2000 | 200 | 1500 | 100 | 500
24 | 24 | 240 | 0 | 2400 | 48000 | 48000 | 360000 | 0 | 0
|  |  | profit | 45600 |  |  | 312000 |  | 0 | 357600 | gallery
[10 empty] | 178800 | 50%
|  |  | costs |  | personal
net income | fte | salaris | 40% | cost / yr | 3 |  |  |  |  | years
3750 | 0.4 | 1500 | 2100 | 25200 | 75600 |  |  |  |  | 4.7302
2.3651